## Gantt Data
Task | TaskID | Parent | StartDate | Duration (days) | EndDate | % Complete | Resource | Milestone
Requirements Gathering | 1 | Planning | 2026-01-06 | 11 | 2026-01-17 | 100% | Business Analyst | 0
Technical Specification | 2 | Planning | 2026-01-17 | 12 | 2026-01-29 | 100% | Architect | 0
Database Design | 3 | Development | 2026-01-29 | 11 | 2026-02-09 | 60% | DB Team | 0
API Development | 4 | Development | 2026-02-09 | 19 | 2026-02-28 | 40% | Backend Team | 0
Frontend Development | 5 | Development | 2026-02-09 | 19 | 2026-02-28 | 50% | Frontend Team | 0
Integration | 6 | Development | 2026-02-28 | 12 | 2026-03-12 | 0% | Dev Team | 0
Unit Testing | 7 | Testing | 2026-02-28 | 19 | 2026-03-19 | 0% | QA Team | 0
Integration Testing | 8 | Testing | 2026-03-19 | 12 | 2026-03-31 | 0% | QA Team | 0
User Acceptance Testing | 9 | Testing | 2026-03-31 | 12 | 2026-04-12 | 0% | Business Users | 0
Production Deployment | 10 | Deployment | 2026-04-12 | 5 | 2026-04-17 | 0% | DevOps Team | 0
Go Live | 11 | Deployment | 2026-04-17 | 0 | 2026-04-17 | 0% | Project Team | 1
Formulas:
EndDate = [StartDate]+[Duration (days)]

## Notes
Field Guide for Power BI Gantt Chart Visual
Task | Task name shown on the Gantt bar.
TaskID | Unique numeric ID per task (useful for sorting/predecessors).
Parent | Group/category name (Planning, Development, Testing, Deployment) — used for grouping/legend.
StartDate | Task start date. Must be a Date field, not a date hierarchy, in Power BI.
Duration (days) | Number of days the task takes.
EndDate | Calculated = StartDate + Duration (formula, not required by the visual but useful for reference/other charts).
% Complete | Decimal between 0 and 1 (e.g. 0.6 = 60%).
Resource | Person/team assigned — shown next to the bar if mapped to the Legend/Resource field.
Milestone | 1 = milestone (zero-duration diamond marker), 0 = normal task.